## Project Scope of Work Template

This Project Scope of Work template has been developed to include the minimum tasks that all Applicants will be required to perform in bold text. The method each Applicant uses to complete each task (milestone) can vary. SANDAG has provided sample milestones that could be used to successfully achieve each task, as shown below. Applicants must update these sample milestones to demonstrate how they will actually complete the task.

| Applicant Name | Full Access and Coordinated Transportation, Inc. (FACT) |
| --- | --- |

| Task #1 | Task/Milestone Description | Deliverables |
| --- | --- | --- |
| 1. | Access Provider Selection and Preparedness | Access Providers ready and able to begin providing on-demand services |
| A. | Identification of third-party Access Providers to provide on-demand WAV services and Consultants: - FACT works with 10 vendors who currently provide on-demand rides for seniors and people with disabilities. We have identified three vendors who are ready to begin providing 60-minute on-demand WAV service under AFA. FACT will include additional Vendors from the existing Brokerage pool and add new ones as AFA demand grows. - Once awarded, FACT will coordinate with members of FACT’s brokerage and those taxi services included on the document request list under the AFA Bid opportunity on Bidnet Direct. - Identify consultants specializing in paratransit operations, training & development, contracting strategies, and sustainability to help develop the detailed operations plan. - Select a mechanic/inspector specializing in transit vehicles and driver requirements - A marketing consultant for developing marketing materials, strategy, and implementation - 1 New staff position - Extension of Call Center Back-up hours with CARS - Develop Software scope of work for a Reservation and Trip Management App (FACT was awarded FTA ICAM funding for app development that will be used to support the AFA project) | Within 7 business days following a Notice to Proceed: - Three (3) vendors will begin providing AFA rides during business and extended hours: - Eleet Transportation, - Furaat Transportation, and - San Diego Medical Transport (SDMed) Within 3 Weeks following a Notice to Proceed: - Additional vendors will be onboarded to plan for growth in demand. - A third-party paratransit consultant will be solicited. - A third-party consultant/mechanic will be solicited to develop a detailed, sustainable operations strategy and streamline service. - A marketing consultant will be solicited to plan and implement a comprehensive outreach and marketing plan. - A new Service Analyst position will be posted – this position will track all AFA service and expense data for reporting and invoicing. - The back up Call center services agreement will be extended 24 hours a day, 7 days a week. - The Software scope of work for a Reservation and Trip Management App will be finalized. |
| B. | Contracting with Additional transportation vendors and Paratransit Consultant: - FACT will work with each vendor to complete necessary CPUC charter-party carrier permit requirements. - FACT will finalize rates and establish contract parameters (e.g., service area and vehicles). Agreements include required pass-through provisions and requirements will be provided for all selected third-party Access Providers. This includes completed background checks, insurance, controlled substance and alcohol testing, Secretary of State registration, and Motor Carrier Profile with California Highway Patrol requirements as required by CPUC regulations. - FACT will establish rates and contract parameters with selected paratransit consultant - FACT will establish rates and contract parameters with the selected mechanic/inspector Interview candidates and select a qualified Service Analyst | Within 6 weeks following the executed grant agreement or Notice to Proceed: - All Additional transportation vendor agreement(s) will be finalized and executed. - A signed third-party agreement meeting all AFA funding requirements will be finalized and executed with the selected transportation consultant. - A signed third-party agreement meeting all AFA funding requirements will be finalized and executed with the selected vehicle inspector (consultant/mechanic). - A Service Analyst will be hired. |
| Task #2 | Task/Milestone Description | Deliverables |
| 2. | Development of Operations Plan | Completed Operations Plan |
| A. | FACT will Conduct a needs assessment on - current demand for WAV services - fleet size and capability, number of trained drivers, etc. FACT will accomplish this assessment by analyzing past service data and client feedback regarding accessible trip supply and demand; WAV shortages has been a longstanding issue in providing equitable transportation solutions. The project will be discussed during regional meetings such as CAM and SSTAC. Regular meetings with each Access Provider will ensure FACT understands the needs of each company to expand WAV capacity. These discussions will assess driver training, insurance expenses, additional vehicles needed and vehicle sharing, etc. Development of draft on-demand WAV services Operations Plan to include: - Description of day-to-day operations - Performance measures to assess daily operations - Techniques to deploy to adapt to changing needs or inability to meet minimum performance measures - Techniques to deploy to improve Response Times or on-demand WAV presence and availability | Within 8 Weeks following a Notice to Proceed: - Completed Report on Needs Assessment Within 10 Weeks following a Notice to Proceed: - A Draft Operations Plan will be developed that details the service, program monitoring, performance measure, etc. - The Plan will include findings from the needs assessment. The plan will also outline the projects outreach and marketing strategy. - The draft will be available for SANDAG and public review. |
| B. | Procurement of WAV-vehicles and other equipment necessary to provide on-demand WAV services (e.g., cameras, software, and software integration) | Within 12 Weeks following the executed grant agreement or Notice to Proceed: - FACT will order 1 accessible hybrid fueled WAV minivan and additional WAV-vehicles if needed, based on the needs assessment and Draft Operation Plan. - Software vendor selection will be completed |
| C. | Development of final on-demand WAV services Operations Plan | Within 12 Weeks following the executed grant agreement or Notice to Proceed: - FACT’s AFA Final Operations Plan will be finalized |
| D. | Vehicles and Inspections | Within 12 weeks following the executed grant agreement or Notice to Proceed: A final list of vehicles will be established; it will be updated regularly to reflect ongoing changes. All vehicles will be thoroughly inspected by the contracted mechanic/inspector before used in FACT’s WAV service. Once the service goes live, FACT’s Safety and Compliance Coordinator will perform vehicle and fit for duty inspections outlined in FACT’s Operations Plan. |
| Task #3 | Task/Milestone Description | Deliverables |
| 3. | Deployment of WAV Service | WAV trips |
| A. | FACT’s On-demand WAV service to Start | Within 7 Weekdays following the executed grant agreement or Notice to Proceed: - FACT will begin providing AFA WAV trips to provisionally eligible members of the public. Trips will be provided throughout the remainder of the grant period concluding no later than June 30, 2023. - On-demand requests and Reservations will be initially accepted by telephone; until the App development is complete. - Initial Request/Reservation hours will be 5am-9pm. - Response time will be 60 minutes after confirmation of request - Fare ($5) will be waived until January 1, 2023 - 60-minute On-demand Rides will be offered during 5am -9pm. 12-hours on-Demand requests will be accepted 24x7 - FACT will stage 4 vehicles in North and South County locations to minimize response time. |
| Task #4 | Task/Milestone Description | Deliverables |
| 4. | Outreach efforts to publicize and promote available on-demand WAV services to disability communities | Completed outreach efforts and well-informed disability communities |
| A. | As the CTSA, FACT is a regional leader in specialized transportation coordination and service delivery. FACT has strong relationships with Center for Independent Living, Braille Institute, Regional Center, NCTD, MTS and social services partners representing the disability community in San Diego. FACT’s partnerships will provide the framework and support to promote the WAV service to the target population. | FACT regularly works with regional agencies that serve special needs individuals, including Center for Independent Living, Braille Institute, SD Regional Center, PACE programs and Parkinsons Association. FACT will partner with these organizations to promote on demand WAV service. FACT manages the Council on Access and Mobility (CAM), a group of 33+ specialized transportation stakeholders including members of the public who meet monthly. The meetings include training and education, industry updates and discussions on service coordination. FACT has partnered with cities/municipal agencies (Oceanside, Escondido, San Marcos), the County of San Diego, hospitals (TriCity, Scripps), non-profit organizations (JFS, Travelers Aid, St. Madeline’s), taxi-cab companies (SDMed, Furaat, Renewing Life), and TNC’s (LYFT). FACT is recognized in the community and has established relationships with many seniors and individuals with disabilities who rely on FACT for their travel needs. Many of these partners would benefit from a reliable WAV service. Examples of relevant agreements and correspondences include Letters of Support from agencies like 211 San Diego and Jewish Family Services, Vehicle Sharing Agreements with NCTD and St. Paul’s Senior Service, Brokerage Agreements with Furaat and Eleet Transportation, and Contracted Service Agreements with the County of San Diego and City of Escondido. FACT also maintains a database of 170+ transportation providers in San Diego County, which can be accessed by anyone searching for transportation options. This requires coordinating with each agency regularly to ensure information is current, accurate, and comprehensive. FACT will provide documentation on the above examples upon request. |
| B. | Deployment of service outreach and marketing strategy outlined in the Operations Plan. This includes the procurement and development of marketing and promotional materials to support outreach efforts | Outreach and marketing will begin at the start of project, but a complete outreach strategy will be implemented, a consultant hired, and all marketing materials will be finalized within three (3) months following the executed grant agreement or Notice to Proceed. FACT’s Operations Plan will outline the Outreach and Marketing Strategy in detail, but outreach activities will include fliers (direct market mailing and partner distribution), community presentations, stakeholder meetings, FACT’s and partner agency website postings, partner referrals (e.g., 211 SD), program workshops, and social media. FACT operates a call center and website referral program, which will provide exposure for, information on, and help users access the new WAV service. FACT has extensive experience marketing services to seniors and individuals with disabilities, such gaining exposure for RideFACT. |
| C. | Outreach Monitoring | Outreach and marketing will continue throughout the project timeline. The effectiveness of outreach activities will be monitored and adjusted based on the response/demand of the target population. |
| Task #5 | Task/Milestone Description | Deliverables |
|  | Monitoring program | Completed reports and monitoring checklist, tracking performance measures |
| A. | Review of Response Times and on-demand WAV presence and availability to ensure reasonableness and consistency with performance measures outlined in Operations Plan | FACT’s Service Analyst will monitor and review response times and on-demand WAV presence and availability monthly to ensure reasonableness and consistency with performance measures outlined in the Operations Plan |
| B. | Deploy strategies to improve Response Times or on-demand WAV presence and availability as described in the Operations Plan | FACT staff will monitor response times over 1 hour and review the information with vendors, to address delays due to driver actions or vehicle availability. We will deploy strategies including assisting vendors with routing, adding new vendors to the AFA program, and seeking new technologies to assist with improving response time. |
| C. | Review of preventative and routine vehicle maintenance to ensure consistency with industry standards, inspection requirements mandated by the CPUC, and other procedures outlined in Operations Plan | FACT’s Safety & Compliance Coordinator will review preventative and routine vehicle maintenance to ensure consistency with industry standards, inspection requirements mandated by the CPUC, and other procedures outlined in the Operations Plan. FACT will maintain the weekly Fit For Duty observations, initial vehicle inspections, and annual inspections as described in the Operations Plan. |
| D. | Deploy strategies to improve routine vehicle maintenance and inspections as described in the Operations Plan | FACT will deploy strategies to improve routine vehicle maintenance and inspections as described in the Operations Plan. These strategies will include updates to the Brokerage Agreement Vehicle Maintenance Standards as applicable, incorporating feedback from our certified mechanic during annual inspections, and providing training resources, including California Association for Coordinated Transportation (CalACT) & Community Transportation Association of America (CTAA) maintenance workshops, to our AFA service providers. |
| E. | Review files for all drivers to ensure compliance with the safety requirements mandated by the CPUC: - Background checks - Driver training - Controlled substance and alcohol testing | FACT’s Safety & Compliance Coordinator will review files for all drivers to ensure compliance with the safety requirements mandated by the CPUC including: - Background checks - Driver Training - Controlled substance and alcohol testing |
| F. | Deploy strategies to ensure compliance with the safety requirements mandated by the CPUC. | FACT will deploy strategies to ensure compliance with the safety requirements mandated by the CPUC including maintaining records for each AFA brokerage vendor on insurance requirements, vehicle inspections, substance and alcohol abuse enrollment, and ongoing weekly Fit for Duty observations along with report checklist. |
| G. | Reporting to SANDAG | FACT will track all required service data and meet all necessary quarterly reporting deadlines. FACT will report service data with monthly requests for reimbursement. FACT has over twelve years of ongoing experience invoicing and reporting to SANDAG for grant funded projects. |
| H. | Project Budget and Schedule Monitoring | FACT will monitor monthly spending to ensure it is in line with budgeted expenses. The project schedule will be monitored to ensure tasks are being completed by the proposed deadline and the project is completed by June 30, 2023. |