## Project Scope of Work Template

This Project Scope of Work template has been developed to include the minimum tasks that all Applicants will be required to perform in bold text. The method each Applicant uses to complete each task (milestone) can very. SANDAG has provided sample milestones that could be used to successfully achieve each task, as shown below. Applicants must update these sample milestones to demonstrate how they will actually complete the task.

| Applicant Name | United Taxi Workers of San Diego |
| --- | --- |

| Task # | Task/Milestone Description | Deliverables |
| --- | --- | --- |
| 1. | Access Provider Selection and Preparedness | Access Providers ready and able to begin providing on-demand services |
| A. | Identification of Taxi Drivers/Access Providers to provide on-demand WAV services | -List of potential Taxi Drivers/Access Providers |
| B. | Procurement of third-party Access Providers | -Copies of agreement(s) including required pass-through provisions and CPUC requirements -List of qualified Access Providers |
| C. | Access Providers complete necessary CPUC charter-party carrier permit requirements | -Every Access Provider has completed background checks, insurance, enrolled in controlled substance and alcohol testing, provided Secretary of State registration, and Motor Carrier Profile with California Highway Patrol requirements as required by CPUC regulations. All Access Providers sign agreement. |
| D. | Procurement of WAV-vehicles or other equipment necessary to provide on-demand WAV services | -Purchase WAV vehicles or vans that can be converted into WAV vehicles (based on availability), and other necessary equipment necessary to provide on-demand WAV services |
| 2. | Development of Operations Plan | Completed Operations Plan |
| A. | Development of draft on-demand WAV services Operations Plan to include, at a minimum: - Assessment of current demand - Assessment of fleet size and capability, number of trained drivers, etc. - Description of day-to-day operations and measures to provide services on a consistent basis - Identification of scalability measures to meet future demand - Performance measures to assess daily operations - Techniques to deploy to adapt to changing needs or inability to meet minimum performance measures - Techniques to deploy to improve Response Times or on-demand WAV presence and availability | -Draft Operations Plan |
| B. | Development of final on-demand WAV services Operations Plan | Completed Final Operations Plan |
| 3. | Outreach efforts to publicize and promote available on-demand WAV services to disability communities | Completed outreach efforts and well-informed disability communities |
| A. | Identification of and development of relationship with partners from disability communities and organizations, as well as other organizations and businesses with disabled members or customers | -List of Disability Orgs we hope to partner with and outreach to -List of Partner Organizations/Unions to outreach to, to offer WAV services -List of Businesses to outreach to, to offer WAV services -List of identified partners and copies of any relevant agreements or other correspondence securing/confirming the relationship |
| B. | Development of outreach strategy | -Completed outreach plan/strategy with efforts to be undertaken, target audience, dates, survey and data collection strategy and any other relevant information |
| C. | Design and procure marketing and promotional materials | -Purchased marketing and promotional materials to support outreach efforts |
| D. | Deployment of outreach strategy | -Completed outreach efforts. Include meeting fliers/agendas and/or meeting summaries/notes |
| E. | Post-Outreach Survey & Data Collection | -Completed survey and summary of responses received, data confirming that Grantee has increased awareness about its on-demand WAV service within its service area |
| 4. | Monitoring program | Completed reports and monitoring checklist, tracking performance measures |
| A. | Review of Response Times and on-demand WAV presence and availability to ensure reasonableness and consistency with performance measures outlined in Operations Plan | Completed report outlining findings. |
| B. | Deploy strategies to improve Response Times or on-demand WAV presence and availability as described in the Operations Plan | Completed report outlining action steps taken to improve performance. |
| C. | Review of preventative and routine vehicle maintenance to ensure consistency with industry standards, inspection requirements mandated by the CPUC, and other procedures outlined in Operations Plan | Completed report outlining findings. |
| D. | Deploy strategies to improve routine vehicle maintenance and inspections as described in the Operations Plan | Completed report outlining action steps taken to improve performance. |
| E. | Review files for all drivers to ensure compliance with the safety requirements mandated by the CPUC: - Background checks - Driver training - Controlled substance and alcohol testing | Completed report outlining findings. |
| F. | Deploy strategies to ensure compliance with the safety requirements mandated by the CPUC. | Completed report outlining action steps taken to ensure compliance. |
| G. | Quarterly Reporting to SANDAG | Completed quarterly reports |