Project Scope of Work Template

This Project Scope of Work template has been developed to include the minimum tasks that all Applicants will be required to perform in grey-shaded, bold text. The method each Applicant uses to complete each task (milestone) can vary. SANDAG has provided sample milestones that could be used to successfully achieve each task, as shown below. Applicants must update these sample milestones to demonstrate how they will complete the task.

## DEFINITIONS

Access Provider means an organization or entity that directly provides, or contracts with a separate organization or entity to provide, On-Demand Transportation to meet the needs of persons with disabilities, as defined in Public Utilities Code Section 5431.5(a).

Fulfilled Trip means a rider requests a trip, the trip is accepted by a provider, and the rider reaches their requested destination.

On-Demand means a transportation service that does not follow a fixed route or schedule, and the provider can fulfill trip requests within twelve hours.

On-Demand Response Time is the time between when a trip is requested and when the passenger is picked up. For on-demand trips, this cannot exceed twelve hours.

Pre-Scheduled Trip Response Time is the time between the passenger’s scheduled pickup time and when the vehicle arrives. If the vehicle arrives before the passenger’s scheduled pickup time, the pickup delay shall be “0”.

Wheelchair-Accessible Vehicle (WAV) means a vehicle equipped with a ramp or lift capable of transporting non-folding motorized wheelchairs, mobility scooters, or other mobility devices, as defined in Public Utilities Code Section 5431.

| Applicant Name | North County Transit District |
| --- | --- |

| Task #1 | Task/Milestone Description | Deliverables |
| --- | --- | --- |
| 1. | Access Provider Selection and Preparedness | Access Providers ready and able to begin providing On-Demand services |
| A. | Identification of Initial Third-Party Access Providers GRANTEE identification of initial third-party Access Providers to provide On-Demand WAV services. | North County Transit District (NCTD) has an existing purchased transportation contract with MV Transportation (MV). MV meets all CPUC requirements and is currently providing NCTD with comprehensive purchased transportation services for all NCTD BREEZE, FLEX, LIFT paratransit, and NCTD+ services. Capacity exists in the contract for MV to provide operations support for On-Demand WAV services planned with proposed expansion of NCTD+. NCTD+ Phase 2 (Vista) is planned for April 7, 2025. Phase 3 (Fallbrook-Pala) is planned for October 7, 2025. If awarded this grant, NCTD could modify start dates to align with NTP and grant parameters. |
| B. | Contracting with Additional Third-Party Transportation Vendors GRANTEE contracting with additional transportation vendors. GRANTEE will coordinate with other providers who could provide AFA service GRANTEE will work with each potential Access Provider vendor to complete the following before the vendor provides AFA service: Meeting the necessary CPUC charter-party carrier permit requirements (or meeting additional requirements if non-permitted) Finalize rates and establish contract parameters (e.g., service area and vehicles). | - Our purchased transportation/Access Provider, MV Transportation has the capacity necessary provide the NCTD+ Phase 2/3 scope. Contracted rates and parameters for this service are set in our existing contract. |

| Task #2 | Task/Milestone Description | Deliverables |
| --- | --- | --- |
| 2. | Additional Support Services and Equipment Selection and Preparedness | Support services were established, and equipment was purchased to assist with On-Demand service. |
| A. | Contracting with Third-Party Paratransit Consultant GRANTEE will identify consultants specializing in paratransit operations, training and development, contracting strategies, and sustainability to help develop or amend the detailed Operations Plan. GRANTEE will establish rates and contract parameters with the selected paratransit consultant. | NCTD is the organization designated to provide complementary paratransit services as required by the ADA. We have 50 years' experience providing high quality wheelchair accessible trips. Our Manager of Paratransit and Mobility Services, Robert Gebo, will lead operations of NCTD+ Phase 2/3. He has decades of experience leading paratransit operations. Additionally, NCTD has an experienced Transit Service Planning team of 5 full-time staff and a Strategic Planning unit of 2 staff that will support the operations planning components of this project. As such, NCTD will not need to contract a 3rd Party Paratransit Consult to develop operations planning for this project. |
| B. | Contracting with Third-Party Vehicle Mechanic/Inspector or Hiring Vehicle Mechanic/Inspector GRANTEE will select a Mechanic/Inspector specializing in transit vehicles and driver requirements to develop a detailed, sustainable operations strategy and streamline service. GRANTEE will establish rates and contract parameters with the selected Mechanic/Inspector. | - NCTD’s existing contract with MV Transportation includes experienced vehicle mechanics, inspection, safety, and quality control positions dedicated to the state-of-good-repair, reliability, compliance, and safety of NCTD+ service. Contracted rates and parameters are outlined in our existing contract. |
| C. | Contracting with Third-Party Marketing Consultant or Hiring Marketing Staff (if applicable) GRANTEE will select a Marketing Consultant or Marketing staff to develop and implement a comprehensive outreach and marketing plan | - NCTD has an existing contract with local DBE firm Cook + Schmid for NCTD+ marketing and communications consulting. Their rates are agreed to and set as part of NCTD’s contract with Spare Labs. - Also, NCTD has dedicated marketing and communications staff available to create marketing and outreach campaigns. This team of 5 positions is led by NCTD’s Chief of Planning and Communications, Chris Orlando and Director of Marketing, Colleen Windsor. - Additionally, NCTD has existing contracts for digital media creation, promotional items, and marketing strategy. NCTD will build off its existing marketing plan and strategy used in NCTD+ Phase 1 to inform NCTD+ Phase 2/3. |
| D. | Identification of Service Analyst GRANTEE will interview candidates and select a qualified person to hire as one new GRANTEE staff position, a Service Analyst, who will track all AFA service and expense data for reporting and invoicing. | NCTD has existing staff qualified to perform the Service Analyst duties. These duties will be performed via NCTD Manager for Paratransit and Mobility Services, Robert Gebo. He will be helped by NCTD’s Finance and Grants team and NCTD Strategic Planning. NCTD’s trip management software provider, Spare Labs, has reports that streamline reporting and analytics. |
| E. | Contracting with Third-Party Backup Call Center GRANTEE will begin backup call center service or extend its backup call center service contract to provide service to requestors during Business Hours and Extended Hours, seven days a week. GRANTEE will respond to requests within Business Hours, and backup call center will respond to requests during Business Hours and Extended Hours. | - NCTD’s existing contract with MV Transportation includes experienced reservationists and dispatcher positions dedicated to NCTD+, LIFT, and FLEX services. This includes 7 day per week bilingual coverage through the NCTD+ service span between 6am and 9pm. Contracted rates and parameters are agreed to in our existing contract. NCTD will continue to provide call center staff throughout the grant to support NCTD+ Phase 2/3. |
| F. | Contracting with Third-Party Trip Management Software GRANTEE will develop or amend its existing reservation and trip management application as needed. | NCTD has an existing Trip Management Software provider for NCTD+/WAV Microtransit, Spare Labs (Spare), NCTD’s contract with Spare was approved in April 2023 and the system is currently deployed in NCTD+ Phase 1 (San Marcos). There is capacity in the existing contract to include NCTD+ Phase 2/3. Spare has white labeled NCTD’s mobile application as NCTD+ and it is currently available in the Apple and Google app stores. Spare also includes a separate interface with Dispatch/Operations, Reservationists, and Analytics/Reporting. |
| G. | Purchase of WAV Vehicles and Other Equipment GRANTEE will procure WAV vehicles and/or other equipment necessary to provide On-Demand WAV services such as cameras, software, and software integration. | NCTD is proposing to use five (5) ADA equipped Ford Transit Vans. Each vehicle has a seated passenger capacity of 8 persons or 2 wheelchairs + 2 additional PCAs or seated passengers. Each vehicle will be branded with NCTD+ vehicle wrap to easily identify the service. These vehicles are available for dedicated use on NCTD+ Phase 2/3 at launch. All vehicles were purchased in 2021 with local source funding at $89,080 each. NCTD proposes to use the value of the vehicles as a match toward project budget. |
| H. | Conducting Vehicle Inspections The GRANTEE’s contracted mechanic/inspector will thoroughly inspect all vehicles before use in GRANTEE’s WAV service. GRANTEE or GRANTEE’s vendor(s) will conduct general daily vehicle inspections Once AFA service goes live, GRANTEE’s Safety and Compliance Coordinator will perform vehicle inspections outlined in GRANTEE’s Operations Plan. | - NCTD’s existing contract with MV Transportation includes experienced vehicle inspection, safety, and quality control positions dedicated to the state-of-good-repair, reliability, compliance, and safety of NCTD+ service. Contracted rates and parameters are agreed to in our existing contract. - NCTD will ensure all inspection and documentation requirements are met per grant requirements. |

| Task #3 | Task/Milestone Description | Deliverables |
| --- | --- | --- |
| 3. | Development of Operations Plan | Completed Operations Plan |
| A. | Conducting Needs Assessment and Development of Draft Operations Plan GRANTEE will conduct a needs assessment on the current demand for WAV services, the fleet size and capability, the number of trained drivers, etc. GRANTEE will accomplish this assessment by analyzing past service data and client feedback regarding accessible trip supply and demand. The project will be discussed during regional meetings such as Council on Access and Mobility (CAM) and the SANDAG Social Services Transportation Advisory Council (SSTAC). GRANTEE will develop a draft On-Demand WAV services Operations Plan to include: Description of day-to-day operations Performance measures to assess daily operations Techniques to deploy to adapt to changing needs or inability to meet minimum performance measures Techniques to deploy to improve Response Times and/or On-Demand WAV presence and availability | NCTD performed a Microtransit Suitability Analysis that was presented to the NCTD Board of Directors in February 2024. The Analysis assessed the suitability of on-demand WAV/Microtransit services across 14 separate conceptual service zones within the NCTD service area in northern San Diego County. The Analysis considered: (1) Equity (2) Transit Connectivity (3) Efficiency (4) Points of Interest. Based on the study’s findings, four service zones were determined to be ‘optimally suitable’ for an on-demand WAV/Microtransit pilot program. These areas were each assigned a phase in NCTD’s Microtransit On-Demand Rides Pilot Program. Phase 1 in San Marcos launched on June 10, 2024. Phase 2/3 are scheduled for calendar year 2025 and Phase 4 in calendar year 2026. Phases 2-4 are subject to availability of NCTD operations funds. NCTD believes this Analysis satisfies the requirement for the WAV Needs Assessment. However, if additional analysis is requested by the GRANTOR, NCTD will commit to completing within 4 weeks of NTP. NCTD currently operates LIFT paratransit and has a full operations plan with extensive policies and procedures related to WAV service. Additionally, NCTD+ Phase 1 launched in June 2024. NCTD uses a slightly modified version of LIFT operations plan/procedures for NCTD+ WAV/Microtransit service. NCTD will document the NCTD+ operations plan for Phase 2/3 and include specific strategies related to marketing and communications in these service areas. NCTD Transit Service Planning, Strategic Planning, Marketing/Comm, and Operations will develop the operations plan for NCTD+ Microtransit Phase 2/3. A draft operations plan will be completed within 4 weeks from NTP. A draft operations plan will be developed that details the service, program monitoring, performance measure, etc. The operations plan will include findings from the needs assessment and outline the project’s outreach and marketing strategy. |
| B. | Development of final Operations Plan | Within 8 weeks following the executed grant agreement or Notice to Proceed: - GRANTEE’s final Operations Plan will be completed. |

| Task #4 | Task/Milestone Description | Deliverables |
| --- | --- | --- |
| 4. | Deployment of WAV Service | WAV trips |
| A. | Providing On-Demand WAV Service to the Public GRANTEE will begin providing On-Demand WAV/Microtransit service to the public. On-Demand requests and reservations will be accepted via call center and NCTD+ mobile application. The application and call center support reservations in English and Spanish language. Service request/reservation hours will be 6:00 a.m. to 9:00 p.m., seven days per week, with a Response Time average of 30 minutes after GRANTEE receives the request. Trips may be requested for immediate dispatch or reserved in advance for the same day of travel. Requests via the NCTD+ can be made starting at 12am for the day of travel only. Reservations via call center can be made daily during revenue service hours (6a-9p) GRANTEE will stage 2 WAV (Phase 2/Vista) and 3 WAV (Phase 3/Fallbrook-Pala) in different locations of the region to minimize Response Time and match demand. | WAV trips can be made 12 weeks after NTP or April 7, 2025, whichever is soonest for Phase 2, Vista. WAV trips can be made 24 weeks after NTP or October 7, 2025, whichever is soonest for Phase 3, Fallbrook-Pala. Since these projects' operational timelines have been set to be mindful of NCTD operational budget constraints, if funding is awarded, NCTD may modify of these timelines to begin service on an accelerated basis. Additionally, the GRANTOR may consider funding arrangements that include operations/financial support for both, Phase 2/3 NCTD+ on-demand WAV/Microtransit or financial support for one phase (Phase 2 – Vista or Phase 3- Fallbrook/Pala). GRANTEE will begin providing AFA WAV/microtransit trips to members of the public in the Phase 2/3 NCTD+ service zones. Budgetary considerations for operations include the following, but not limited to: - Compensation and benefits for NCTD+ operators, dispatchers, reservationists, supervisors, mechanics, and cleaners. - Vehicle Fuel - Vehicle Parts - Vehicle Inspections - Materials - Insurance Phase 2 – Vista operations budget is based on estimated 10,950 service hours during the 12-month pilot. Actual service provided will be based on demand. Phase 3 – Fallbrook/Pala operations budget is based on estimated 16,425 service hours during the 12-month pilot. Actual service provided will be based on demand. Total service: 27,375 hours |

| Task #5 | Task/Milestone Description | Deliverables |
| --- | --- | --- |
| 5. | Outreach efforts to publicize and promote available On-Demand WAV services to disability communities | Completed outreach efforts and well-informed disability communities |
| A. | Preliminary AFA Outreach and Marketing Preliminary AFA outreach will consist of meetings with key stakeholders in each NCTD+ service area. This includes the City of Vista, San Diego County, NCTD Board of Directors, Palomar College and other higher level educational institutions. | Within 6 weeks of the Notice to Proceed: Preliminary AFA outreach and marketing will begin |
| B. | Development and Deployment of Marketing Outreach with Third-Party Marketing Consultant GRANTEE and its marketing consultant will develop a marketing campaign and related materials to publicize and promote GRANTEE’s On-Demand WAV/Microtransit services to disability communities in low-income and minority areas and populations with limited English proficiency. GRANTEE’s Operations Plan will detail the complete outreach and marketing strategy. Outreach activities will include fliers (direct market mailing and partner distribution), community presentations, stakeholder meetings, GRANTEE and partner agency website postings, partner referrals, program workshops, and social media. GRANTEE will also advertise and market the service through its call center and website referral program. | Within 12 weeks of following the Notice to Proceed: A complete outreach strategy will be implemented All marketing materials will be finalized and utilized to advertise the service GRANTEE and its marketing consultant will conduct the following activities under a 6-month marketing campaign to publicize and promote the GRANTEE’s On-Demand WAV/Microtransit services: Produce a photoshoot/video shoot that will be published on the GRANTEE’s website and advertised using social media and paid media. Develop a press release to announce the service to local media. Community launch event and ribbon cutting ceremony. On-board transit vehicle advertising Community drop-ins and pop-up events at higher education locations, senior centers, medical arts complexes/hospitals, civic centers, parks/recreation areas, other locations to be identified as part of comprehensive marketing strategy. Once AFA service begins, conduct targeted outreach and follow-ups, and provide a high-level report of press release pickup, coverage, and media conversations. Outreach and marketing of AFA service will continue throughout the grant term. NCTD recently launched NCTD+ Phase 1 in San Marcos. Public engagement was extensive and included postcard mailer to 28,000 residents, gas pump topper advertising, community pop-ups, press conference and community ribbon cutting ceremony, social media, partner tool kits, flyers, roadside billboard, A-frames at NCTD transit centers, and more. NCTD will use a similar scale marketing strategy for Phase 2/3 if awarded in this submittal. Many items for marketing collateral have already been developed as part of Phase 1 and can be easily adapted and updated for Phase 2/3. |
| C. | Adjustments to Outreach Activities The effectiveness of outreach activities will be monitored and adjusted by GRANTEE based on the response/demand of the target population. GRANTEE will ensure that: Its On-Demand WAV services are effectively publicized and promoted to disability communities It markets and promotes public awareness of its On-Demand WAV services in both low-income and minority areas as well as populations with limited English proficiency Its services are made available to individuals who do not have a smartphone or internet or need additional assistance in requesting the service | GRANTEE will adjust its outreach strategy to ensure the services are publicized and promoted to disability communities within the WAV/Microtransit service area. |
| Task #6 | Task/Milestone Description | Deliverables |
| 6. | Monitoring program | Completed reports and monitoring checklist, tracking performance measures |
| A. | Adjustments to On-Demand WAV Service GRANTEE will review its Response Times and On-Demand WAV presence and availability and deploy strategies to ensure reasonableness and consistency with performance measures outlined in the Operations Plan and to ensure that Response Times are comparable to what a non-WAV on-demand requestor would receive on the same or comparable service. Every month, GRANTEE’s will monitor and review Response Times and On-Demand WAV presence and availability to ensure reasonableness and consistency with performance measures outlined in the Operations Plan GRANTEE will deploy strategies that improve its Response Times or On-Demand WAV presence and availability as described in the Operations Plan | As a transit provider, NCTD consistently performs monitoring and analysis of our services. A fully staffed Service Planning, Strategic Planning, and Operations Departments work collaboratively to review performance and make appropriate adjustment to ensure service is best serving area residents. Monthly report that describes Response Times and On-Demand WAV presence and availability of GRANTEE and its Access Providers. Every month, GRANTEE will monitor Response Times exceeding one hour and review the information with the relevant Access Provider(s) to address delays due to driver actions or vehicle availability. GRANTEE will deploy strategies to improve Response Times, including but not limited to: Assisting Access Providers with identifying the most time-effective route to take Increasing dedicated service availability to meet demand and reduce wait times. Seeking new technologies used by transit operators or other specialized transportation providers to improve service |
| B. | Compliance Monitoring of Vehicles GRANTEE’s Safety & Compliance Coordinator will review the preventative and routine vehicle maintenance performed by Access Providers to ensure consistency with industry standards, inspection requirements mandated by the CPUC, and other procedures outlined in the Operations Plan. GRANTEE will maintain the weekly vehicle observations, initial vehicle inspections, and annual inspections as described in the Operations Plan. | As a transit operator, NCTD is familiar with and currently has operations procedures and resources in place to ensure proper inspection and state-of-good-repair of vehicles placed in revenue service. GRANTEE will provide a quarterly report outlining the findings of GRANTEE’s review of preventative and routine vehicle maintenance. The report will also include any issues reported to GRANTEE by an Access Provider and any complaints received by GRANTEE or an Access Provider regarding AFA service. GRANTEE will deploy strategies to improve routine vehicle maintenance and inspections as described in the Operations Plan. These strategies will include: Incorporating feedback from the certified mechanic during annual vehicle inspections Providing training resources to Access Providers, including California Association for Coordinated Transportation (CalACT) and Community Transportation Association of America (CTAA) maintenance workshops. |
| C. | Compliance Monitoring of Drivers and Other CPUC Safety Requirements GRANTEE will review Access Provider files for all drivers who provide AFA service to ensure compliance with the safety requirements mandated by the CPUC: Background checks Driver training Controlled substance and alcohol testing GRANTEE will deploy strategies to ensure compliance with the safety requirements mandated by the CPUC, including random requests for Access Providers to provide documentation for their drivers. | As a transit operator, NCTD is familiar with and currently has operations procedures and resources in place to ensure compliance monitoring of drivers and CPUC safety requirements. NCTD has a Safety Division that is uniquely qualified to provide oversight on all NCTD revenue service operations by our purchased transportation provider, MV Transportation. GRANTEE will deploy strategies to ensure its Access Providers comply with the safety requirements mandated by the CPUC, including maintaining records for insurance requirements, vehicle inspections, controlled substance and alcohol testing, driver training, and ongoing weekly vehicle observations. GRANTEE will require its Access Providers to retrain and certify any driver that fails to meet the safety requirements mandated by the CPUC before the driver is permitted to provide AFA service. GRANTEE will provide a quarterly report that includes the data compiled during the previous three-month period, including whether any complaints were filed against an Access Provider or its drivers. |
| D. | Quarterly Reports GRANTEE will track all required service data and meet all necessary quarterly reporting deadlines. | Every quarter and as described in the AGREEMENT, GRANTEE will provide to SANDAG: CPUC Quarterly Data Report SANDAG Quarterly Status Report |
| E. | Project Budget and Schedule Monitoring | GRANTEE will monitor its monthly spending to ensure alignment with budgeted expenses. The project schedule will be monitored to ensure tasks are being completed on time and the project is completed by the grant termination date. |